CodeForge: Rise of Solvers

Team Work Split & Accelerated Schedule

Group 7 - IIIT Kottayam  |  Prepared August 13, 2026

# 1. Work Split — Person → Module Assignment

Modules are grouped so each person owns full-stack work (backend module + matching frontend feature) for their lane, minimizing cross-person handoffs. Grouping follows the SADD's M1–M9 module decomposition rather than splitting evenly, so each lane reflects a real dependency boundary, not just a headcount split.

| Person | Owns | Why This Grouping |
| --- | --- | --- |
| P1 — Foundation | M1 Auth, M9 Admin/Config, repo infra (CI, Docker, deploy) | M1 is the hard blocker for everyone else — needs to ship first, fast. M9 is low-dependency CRUD, a good fit for whoever is also babysitting infra. |
| P2 — Core Engine | M2 Platform Sync (judge adapters), M3 Village | M3 directly consumes M2's output (topic progress → village levels). Same-person ownership means no cross-person handoff for that data flow. |
| P3 — Battle Systems | M4 Attacks, M7 League & Trophy | M7's trophy events are driven almost entirely by M4's attack outcomes (win/loss/defense). Same-person ownership avoids a two-person sync tax on every trophy rule change. |
| P4 — Guild & Realtime | M5 Guild & Territory, M6 War Room, M8 Notifications | M6 is a read view on top of M5's data, and M8 (WebSocket gateway) is needed earliest by guild/territory events (live zone changes) — bundling it here means P4 builds the realtime pipe once and everyone else just publishes to it. |

Dependency chain: M1 → M2 → M3 → {M4, M5} → {M6, M7}. M8 must exist early (even as a stub) since M4, M5, and M6 all publish through it.

This is a starting assignment based on module dependencies, not a judgment on who should do what — swap names in freely; the module logic is what matters, not the labels.

# 2. Sync Points — the “Obviously Connected” Parts

These are the only moments the team must coordinate. Outside of these four checkpoints, each person can work in their own module folder without waiting on anyone.

| Date | Sync Point | What Happens |
| --- | --- | --- |
| Aug 20, 2026 | Auth contract freeze | P1 publishes the final /auth request/response shapes and how a JWT/session is validated. Everyone else codes against that contract from here on. |
| Aug 27, 2026 | Village data contract freeze | P2 publishes the shape of a “topic progress” object. P3 and P4 both need this (attacks read weak topics, territory reads aggregate scores). |
| Sep 3, 2026 | WebSocket event schema freeze | P4 publishes the event payload shapes (attack notification, territory change, war-room update) — matches SADD Appendix B.1. P3 and P4 both emit through this. |
| Sep 10, 2026 | Integration day | Everyone merges into develop and the four modules get wired together for the first time as a whole app. |

# 3. Master Schedule — Internal Targets vs. Official Sheet

Starting from Aug 13, running the same 30% / 60% / 80% / integrate / test / deploy / document sequence as the official timeline, but compressed roughly one week ahead at every milestone.

| Sprint | Our Dates | Our Target | Official Deadline | Buffer |
| --- | --- | --- | --- | --- |
| Sprint 0 | Aug 13–17 | Repo scaffold, DB schema draft, task board set up | (not on official sheet) | — |
| Sprint 1 | Aug 18–24 | 30%: Auth working end-to-end, all module DB models stubbed, one live judge adapter (Codeforces), village level calc, WebSocket skeleton, admin config skeleton | Aug 25 / Sep 1, 2026 | ~1 week |
| Sprint 2 | Aug 25–31 | 60%: full judge linking + verification, all 3 judge adapters, village dashboard rendering, matchmaking + curated problem sets, guild create/join + territory scoring, real events flowing over WebSocket | Sep 8, 2026 | ~1 week |
| Sprint 3 | Sep 1–7 | 80%: War Room, league/trophy + promotion logic, admin panel, cooldown enforcement, frontend polish across all features | Sep 15, 2026 | ~1 week |
| Sprint 4 | Sep 8–14 | Integration: all modules wired end-to-end, cross-module bug bash | Sep 22, 2026 | ~1 week |
| Sprint 5 | Sep 15–21 | Testing: unit/integration/system tests, fix defects, Test Report drafted | Sep 29, 2026 | ~1 week |
| Sprint 6 | Sep 22–28 | Deploy: real host (not localhost), demo running on a machine that isn't the developer's | Oct 6, 2026 | ~1 week |
| Sprint 7 | Sep 29–Oct 5 | Docs: finalize SRS/SADD, User Manual, final presentation deck | Oct 13, 2026 | ~1 week |
| Buffer | Oct 6–20 | Pure buffer — polish, rehearsal, address any late feedback | Oct 13–20, 2026 (official final demo) | 2 full weeks spare |

# 4. Weekly Per-Person Breakdown

Detailed task assignments for each sprint, by person. Each row is one week; each column is one person's concrete deliverables for that week.

| Sprint | P1 — Auth/Admin | P2 — Sync/Village | P3 — Attacks/League | P4 — Guild/Realtime |
| --- | --- | --- | --- | --- |
| Sprint 0 (Aug 13–17) | Set up repo scaffold, CI pipeline, Docker Compose baseline | DB schema draft for Topic / VillageTopicProgress | DB schema draft for Attack / Trophy | DB schema draft for Guild / Territory; WebSocket connection manager skeleton |
| Sprint 1 (Aug 18–24) | Register/login/JWT endpoints; judge-link verification flow; FREEZE auth contract (Aug 20) and publish to team | Codeforces adapter (fetch + parse); topic-level calc from solve history | Stub matchmaking (random target); cooldown model (schema only) | Guild create/join models; publish a test event end-to-end through M8 |
| Sprint 2 (Aug 25–31) | Link/unlink additional judges; session management (7-day persistence, logout) | LeetCode + CodeChef adapters; village dashboard rendering; FREEZE village data contract (Aug 27) | Real matchmaking (comparable-strength targets); curated problem-set generation from weak topics | Territory scoring aggregation; zone ownership updates; guild join approve/reject flow |
| Sprint 3 (Sep 1–7) | Admin panel: manage users/guilds; attack/cooldown rule config (UC-11, UC-12) | Sync-status indicator UI; graceful handling of unavailable/rate-limited judges | Attack scoring + outcome notification; trophy count adjustment; league tier promotion/demotion | War Room: per-member topic-strength summary; FREEZE WebSocket event schema (Sep 3) |
| Sprint 4 (Sep 8–14) | Integration support: auth edge cases surfaced by other modules | Integration support: sync/village edge cases | Integration support: attack/league edge cases | Integration support: guild/realtime edge cases; INTEGRATION DAY (Sep 10) — merge all into develop |
| Sprint 5 (Sep 15–21) | Unit + integration tests for M1/M9; fix defects | Unit + integration tests for M2/M3; fix defects | Unit + integration tests for M4/M7; fix defects | Unit + integration tests for M5/M6/M8; fix defects; compile Test Report |
| Sprint 6 (Sep 22–28) | Deploy backend + Postgres/Redis to real host; env/secrets setup | Verify judge sync works against real host (not localhost) | Load-test matchmaking + attack scoring on deployed environment | Deploy frontend; verify WebSocket works over real network; run full demo pass |
| Sprint 7 (Sep 29–Oct 5) | Finalize SRS/SADD sections owned; User Manual — auth & admin | User Manual — sync & village | User Manual — attacks & league; presentation deck draft | User Manual — guild & realtime; assemble final presentation deck |

Note: This is a starting plan. Update the module ownership, sync-point dates, and weekly targets as the team's actual pace becomes clear — the goal is staying ~1 week ahead of the official timeline, not hitting these exact dates.